## 1. Inputs
Barefoot Addo — Build Cost & Risk Model (INTERNAL)
Yellow = input. Orange = TBC (my estimate until Abel/Gerhard confirms). Every other sheet reads from here. Ex VAT unless stated. 29 Sep 2026.
A. Commercial
VAT rate | 15% | SARS
Target sell price to client (incl VAT) | 335000 | 29 Sep: client schedule generated at R335,000 (15.2% GP at current inputs). Change to test.
Vodacom BC 100 Mbps 36m — CTTX cost / month | 4152.04 | Fixed Services AAG 092026 (Duane, 14 Sep 2026)
Vodacom markup | 20% | Gerhard: 20% on this deal (policy recommends 25% for 100 Mbps)
Vodacom 3rd-party site surcharge / month (cost) | 0 | AAG: '3rd-party infrastructure will incur additional cost'. Olifants Nek = Telkom site. Asked Duane 29 Sep.
Vodacom installation (NRC) — cost | 2607.83 | AAG 092026
CTTX managed-service retainer / month (client, ex VAT) | 1500 | Gerhard, 26 Sep
Client's current monthly bill (incl VAT) | 18105.6 | Herotel invoice 8313058, 31 Aug 2026
Client finance rate p.a. (if they apply for rent-to-own) | 12% | Gerhard's expectation, 29 Sep — client applies directly; CTTX is paid cash
Finance term (months) | 36
B. Quantities (scenario switches)
Base station radios (ePMP 4500L) | 2 | Abel BOM 29 Sep
Sector antennas 90/120° | 2 | Abel BOM
Subscriber radios — lodge/villa/spa/school/workshop cluster (excl. staff village) | 15 | Abel: 25 total, of which 10 are the staff village at 2.3–3 km
Subscriber radios — staff village (10 houses) | 10 | SWITCH: set to 3 if Abel confirms clustering on LAN
Staff-village LAN cable if clustered (metres, total) | 0 | SWITCH: only when staff radios < 10. Abel to give run lengths.
Outdoor Wi-Fi 6 APs | 4 | SWITCH: Abel's BOM says 25; my challenge says ~4 (villa, main lodge, boma). Abel to confirm.
Indoor Wi-Fi 6 ceiling APs | 22 | Total APs = 26 (Abel: 25 + 1). Indoor = 26 − outdoor.
Managed 8-port PoE+ switches | 2 | Abel BOM
Unmanaged 6-port PoE switches | 2 | Abel BOM
4U wall boxes | 4 | Abel BOM
Mast height (enter 6 or 9) | 6 | SWITCH: Abel proposes 6m. 9m is the surveyed/safe height. Duane to confirm LOS at 6m.
Outdoor cable per subscriber site (m) | 40 | Gerhard: average 40m per site (the 25 Sep quote wrongly carried 40m TOTAL)
Installation days (2-technician team) | 4 | Gerhard, 29 Sep: 4 days for 25–28 radios (was 3)
Overnight stays (nights) | 0 | Assumed day trips (1h45 each way). Risk register carries the exposure.
Include extended warranties? (1 = yes, 0 = no) | 0 | Abel added 2-yr extensions; not priced on Duxnet V2. Recommend 0 (offer as option).
C. Unit costs (ex VAT)
ePMP 4500L 5GHz AP | 8470 | Duxnet DUX00455421 V2, 25 Sep — in stock
ePMP sector antenna 90/120° | 3209 | Duxnet V2 — in stock
ePMP Force 4525L SM 25dBi | 2745 | Duxnet V2 — Gerhard: in stock and secured (29 Sep)
DuxNet Wi-Fi 6 ceiling AP | 1025 | Duxnet V2
DuxNet outdoor Wi-Fi 6 AP | 1885 | Duxnet V2 — 84% more than indoor
DuxNet 8-port PoE+ L2 cloud switch | 1899 | Duxnet V2
Unmanaged 6-port PoE switch | 650 | TBC — Abel/Duxnet
4U wall box | 600 | TBC — Abel
Ext. warranty 2 yrs — 4500L (each) | 0 | TBC — not on Duxnet V2
Ext. warranty 2 yrs — 4525L (each) | 0 | TBC — not on Duxnet V2
Solar kit: 2×660W Aiko, Victron MPPT 150/35, 5.32kWh LFP, Solis 5kW off-grid, DB components | 25950.82 | Herholdt's PLZ-Q488632, 29 Sep — valid 7 days, cash
Outdoor cabinet, bare (CTTX stock) | 8000 | Gerhard, 29 Sep: floor R8,000 - confirmed
6m mast with plinth, installed (CTTX stock) | 22000 | Gerhard, 29 Sep: floor R22,000 - confirmed
9m mast with plinth, installed (CTTX refurbished stock) | 38700 | Gerhard, 25 Sep
Radio bracket | 450 | Gerhard, 25 Sep
Outdoor cable per metre | 12 | Gerhard, 25 Sep (rate card says R28–45/m for armoured — risk)
LAN cable + trenching per metre (staff-village clustering) | 0 | TBC — only if clustering is chosen
Labour: survey & design (day) | 4500 | CTTX rate card
Labour: installation, 2-tech team (day) | 9000 | CTTX rate card
Labour: commissioning & testing (day) | 4500 | CTTX rate card
Labour: documentation & handover (half day) | 2250 | CTTX rate card
Overnight stay, 2 techs (per night) | 1800 | Estimate — no rate on file

## 2. Cost Build-up
Cost build-up at the current scenario
All formulas read from '1. Inputs'. Change a switch there and this recalculates.
Line item | Qty | Unit cost | Line cost | TBC? | Source / note
1. Backbone (mast, sectors, base radios)
ePMP 4500L base station radio
Sector antenna 90/120°
Mast with plinth, installed (6m or 9m per switch) | 1 |  |  | TBC | 6m cost is an estimate; LOS at 6m unconfirmed
Ext. warranty — 4500L |  |  |  | TBC
Backbone subtotal
2. Distribution (subscriber radios to buildings)
Force 4525L subscriber radio — main cluster
Force 4525L subscriber radio — staff village |  |  |  | TBC | 10 today; 3 if clustered on LAN
Radio brackets
Outdoor cable (per-site average × sites) |  |  |  |  | R12/m is below rate card for armoured cable — see risk
Staff-village LAN cable + trenching (only if clustered) |  |  |  | TBC
Ext. warranty — 4525L |  |  |  | TBC
Distribution subtotal
3. Wi-Fi & switching
Indoor Wi-Fi 6 ceiling AP
Outdoor Wi-Fi 6 AP |  |  |  | TBC | Abel's BOM has 25 outdoor; challenge says ~4
Managed 8-port PoE+ switch
Unmanaged 6-port PoE switch |  |  |  | TBC
4U wall box |  |  |  | TBC
Wi-Fi & switching subtotal
4. Power
Solar kit (Herholdt's Q488632) | 1 |  |  |  | Quote valid to 6 Oct; cash terms
Outdoor cabinet, bare | 1 |  |  | TBC
Power subtotal
5. Labour & travel
Survey & design | 1
Installation — 2-technician team (days)
Commissioning & testing | 1
Documentation & handover | 1
Overnight stays |  |  |  | TBC
Labour & travel subtotal
TOTAL BUILD COST (ex VAT)
of which TBC lines (estimates)
Sell price to client (ex VAT)
Sell price to client (incl VAT)
GROSS PROFIT on the build (ex VAT)
GP %
Comparison: 25 Sep quote cost R264,084 → sold at R308,695.65 ex (R355,000 incl) → GP R44,611.65 (14.5%).
Recurring margin (not in the build GP): Vodacom markup + retainer, see '4. Client ROI'.

## 3. Risk Register
What is our risk at this price? — every open item as rand exposure against the GP
Probability = input (yellow). Exposure is calculated from the Inputs. Expected = probability × exposure. Worst case = everything hits at once.
Risk | Probability | Exposure (ex VAT) | Expected cost | Mitigation / who closes it | Status
Mast: 6m has no usable LOS → build 9m. Gerhard stood at the mast position 29 Sep and saw clear LOS to Olifants Nek at ground level; Vodacom's own confirmation at 6m and Abel's 3 km staff-village LOS remain. | 15% |  |  | Vodacom desktop confirmation (Duane, asked 29 Sep); Abel: staff village LOS at 6m | REDUCED
6m mast cost - CONFIRMED R22,000 (Gerhard 29 Sep) | 0% |  |  | Gerhard prices from stock | CLOSED
Bare cabinet cost - CONFIRMED R8,000 (Gerhard 29 Sep) | 0% |  |  | Gerhard prices from stock | CLOSED
Outdoor APs: Abel insists on 25 outdoor, not 4 | 35% |  |  | Abel confirms which buildings need outdoor units | OPEN
Staff-village clustering NOT feasible (stay at 10 radios) — only if the scenario assumes 3 | 50% |  |  | Abel: house spacing, trenching | OPEN
Cable: armoured grade required (R30/m vs R12/m) | 40% |  |  | Abel confirms grade at survey; rate card says R28–45/m | OPEN
Installation overruns by 1 day beyond the planned 4 | 25% |  |  | Plan 4 days; or accept as GP erosion | REDUCED
Overnight stays needed (3 nights, 2 techs) | 40% |  |  | Confirm with Abel; day trips are 3h30 round trip | OPEN
Extended warranties expected by client at no extra charge | 20% |  |  | Price them; offer as option — currently R0 as TBC | OPEN
Unmanaged switches / wall boxes cost more than estimated | 40% |  |  | Abel prices from Duxnet/Pinnacle | OPEN
Herholdt's quote lapses (7 days) and re-prices up 10% | 30% |  |  | Order on deposit receipt; or re-quote | OPEN
Duxnet price change on exchange rate before order (5%) | 30% |  |  | Duxnet: 'prices valid only for in-stock items, subject to exchange rate'. Order promptly. | OPEN
Vodacom 3rd-party surcharge at Olifants Nek — CTTX absorbs it for the 36-month term rather than re-open the price | 30% |  |  | Asked Duane 29 Sep. If confirmed before quoting, it goes into the MRC, not our margin. | OPEN
Vodacom feasibility FAILS after build — client keeps current link; retainer only (lost Vodacom margin over 36m) | 15% |  |  | Make the order conditional on desktop feasibility; the build still stands on its own | OPEN
Expected risk cost (sum of probability × exposure)
Worst case (every risk hits)
GP at the target price (from sheet 2)
GP after EXPECTED risk
GP in the WORST case
How to read this: if 'GP after expected risk' is still positive and acceptable, R305k is a price we can stand behind once the TBC lines are confirmed. If 'worst case' is negative, that is the amount we must protect with conditions (feasibility first, deposit before order, 4-day install in the labour line) or with a higher price.

## 4. Client ROI
Client view at this price — outright vs their own finance
Incl VAT. Current bill from Herotel invoice. CTTX monthly locked 36 months, then 8%; current provider +8%/yr from year 2 (assumption).
Vodacom BC 100 Mbps client MRC (incl VAT)
CTTX retainer (incl VAT)
New monthly bill (incl VAT)
Saving per month vs today
Upfront: build + Vodacom NRC (incl VAT)
Simple payback (months)
Year-by-year (cumulative, incl VAT)
| Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5
Current provider cumulative | Year 0: 0
CTTX path cumulative (upfront at year 0)
Cumulative saving (current − CTTX)
36-month net (end of agreement)
5-year net
If the client finances the build themselves (they apply directly; CTTX is paid cash)
Finance rate p.a.
Term (months)
Monthly instalment on the build (incl VAT)
Total monthly during the term (instalment + connectivity + retainer)
Versus today's bill (negative = cheaper than now)
Total finance cost over the term
Monthly after the term (network owned)

## 5. Scenarios
Price × scenario — GP on the build (snapshot values, ex VAT; live model is sheets 1–3)
Cost scenarios: (a) Abel's BOM as sent (25 outdoor APs, 10 staff radios, 40m cable total, my TBC estimates); (b) model defaults (4 outdoor APs, 10 staff radios, 40m cable per site, TBC estimates); (c) all levers land (3 staff radios + 300m LAN, 6m mast R20k, bare cabinet R6k, 4 outdoor APs).
Cost scenario → GP (GP%) | Sell R305,000 incl | Sell R325,000 incl | Sell R345,000 incl | Sell R355,000 incl
(a) Abel BOM as sent cost R258,562 | R6,655 (2.5%) | R24,047 (8.5%) | R41,438 (13.8%) | R50,134 (16.2%)
(b) Model defaults cost R252,022 | R13,196 (5.0%) | R30,587 (10.8%) | R47,978 (16.0%) | R56,674 (18.4%)
(c) All levers land cost R221,797 | R43,421 (16.4%) | R60,812 (21.5%) | R78,203 (26.1%) | R86,899 (28.2%)
Price that holds 14.5% GP:
(a) Abel BOM as sent | R347,773 incl VAT
(b) Model defaults | R338,977 incl VAT
(c) All levers land | R298,323 incl VAT
Reading: R305k only holds our margin if scenario (c) lands — staff-village clustering AND stock-priced mast/cabinet. At the model defaults, R345k is the price that keeps 14.5%; R305k leaves R13k before risk and goes negative after expected risk (sheet 3).