## 1. Business Case
Barefoot Addo Elephant Lodge — Own-Network Business Case
Why build a private carrier-grade network instead of continuing to rent one, month after month, forever.
Prepared for: Barefoot Addo Elephant Lodge (Pty) Ltd owners (Port Elizabeth)
Prepared by: Gerhard Smit, CTTX Services (Pty) Ltd
Date: 26 September 2026
The Simple Version
Right now the lodge pays a monthly bill to Herotel forever, for equipment it will never own, on a network it does not control. This proposal is the alternative: pay once to build a private network on your own engineered mast, then pay a much smaller monthly fee for the carrier link that feeds it. The network is built to run for 10 years, and CTTX supports it for that whole period.
Headline Numbers
One-time build cost (infrastructure, owned by the lodge)
Current Herotel monthly bill (connectivity + rented Wi-Fi equipment)
New monthly bill once built (Vodacom link + CTTX monitoring - recommended)
Monthly saving once built
Time to pay back the build cost
Total saved over 10 years vs staying with Herotel
Why This Makes Sense Over 10 Years
1. The lodge currently pays for connectivity AND for the right to use someone else's Wi-Fi equipment, every month, indefinitely. Nothing is ever owned.
2. The existing backhaul radios are mounted on a leaning gum pole - not an engineered structure. That is a physical failure risk, separate from the cost problem.
3. Building a private network converts a forever-rising monthly rental into a one-time build cost plus a much smaller ongoing carrier fee for just the connectivity - the Wi-Fi equipment, the mast, and the solar power all become the lodge's own asset.
4. CTTX designs, builds, and supports this network for an expected 10-year working life - see tab 5 for what that support includes and excludes.
5. See tab 4 for the year-by-year numbers: the build cost is recovered from the monthly saving within the payback period shown above, and every month after that is money the lodge keeps instead of sending to a telecoms reseller.
Full cost detail: tab 2 (build cost), tab 3 (monthly comparison), tab 4 (10-year cash flow), tab 5 (assumptions - read this before trusting any number on this page).

## 2. CAPEX Build Cost
One-Time Build Cost (CAPEX)
All prices exclude VAT unless marked. Source: Duxbury Networking Quote DUX00455421 v2 + CTTX rate card + CTTX labour estimate.
Hardware BOM
Item | Model | Qty | Unit Price | Total
Backhaul Base Station | Cambium ePMP 4500L 5GHz AP, 2x2, AC PoE | 2 | 8470
Sector Antenna | ePMP Sector Antenna 5GHz 90/120deg | 2 | 3209
Subscriber Modules | Cambium ePMP Force 4525L, 25dBi | 28 | 2745
Indoor Access Points | DuxNet Wi-Fi 6 Ceiling AP, 1Gb WAN/LAN | 28 | 1025
Outdoor Access Points | DuxNet Outdoor Dual-Band Wi-Fi 6 AP | 2 | 1885
Network Switches | DuxNet 8-Port Gigabit PoE+ L2 Cloud Switch | 4 | 1899
Hardware Subtotal
Outdoor Infrastructure & Civil
Not standard rate-card items - priced as supplier/stock quotes specific to this site (per Gerhard, confirmed 25-26 Sept 2026).
Item | Model | Qty | Unit Price | Total
9m Steel Mast with Plinth, installed | CTTX second-hand stock; replaces existing gum-pole mount | 1 | 38700
Outdoor Cabinet | w/ MPPT Charge Controller & Lithium Battery Switchgear | 1 | 28670
Solar Panels | Canadian Solar 680W Monocrystalline | 4 | 2200
Grid/Solar Inverter |  | 1 | 2150
Outdoor Cabling | Mast-to-cabinet, WAN, AP runs (avg. 40m run - confirm at survey) | 40 | 12
Mounting Brackets & Hardware | Radio, AP, and solar mounts | 15 | 450
Infrastructure Subtotal
Labour
Task | Notes | Days/Units | Rate | Total
Site survey and design | 1 day | 1 | 4500
Installation (AP deployment, cabling, PoE, switch config) | 2-tech team, 3 days | 3 | 9000
Commissioning and testing | 1 day | 1 | 4500
Documentation and handover | 1 half-day | 1 | 2250
Labour Subtotal
Travel/accommodation not applied - day-trip distance from PE assumed; confirm at survey.
Trenching: not applicable - wireless solution, no underground civil works required.
Project Total
Subtotal (Hardware + Infrastructure + Labour)
Contingency |  |  | 10%
Project Total (Excl. VAT)
VAT |  |  | 15%
TOTAL BUILD COST (Incl. VAT)

## 3. Monthly Cost Comparison
Monthly Cost — Current (Herotel) vs Proposed (CTTX)
Herotel figures from Tax Invoice #8313058, dated 31 Aug 2026. CTTX/Vodacom figures are the confidential-cost-protected client price from the CTTX Vodacom Reseller Pricing Master (Notion, updated 15 June 2026) - never the underlying CTTX cost.
Current: Herotel Business (what the lodge pays today)
Item | Excl. VAT | Incl. VAT
Business WTTB 100 Mbps Symmetrical | 9999 | 11498.85
Static IP | 180 | 207
Huawei Wi-Fi 6 AP 362 (Managed-lite, 9x 24-month term) | 2061 | 2370.15
HB Managed Wi-Fi (Lite) 0-5 (x2) | 298 | 342.7
Huawei Wi-Fi 6 AP 362 (Managed-lite, 14x 12-month term) | 3206 | 3686.9
Herotel Monthly Total (current)
Proposed: Vodacom Business Connect via CTTX (carrier connectivity only)
Uncontended (1:1), Uncapped, Unshaped, No FUP, Symmetrical, Business SLA, Huawei router included, 1 static IP standard. 24-month contract. Subject to feasibility confirmation.
Item | Excl. VAT | Incl. VAT
Vodacom Business Connect 100 Mbps (Monthly Recurring Charge) | 7103 | 8168
Once-off Connection Fee (NRC) - not monthly, shown for reference | 3130 | 3599
Vodacom-Only Monthly Total
Optional Add-On: CTTX Managed Service Retainer (recommended)
Remote monitoring (Cambium cnMaestro + Victron), proactive maintenance, quarterly on-site visits, battery/solar health checks, priority emergency support. CTTX does not deploy unmonitored infrastructure as a matter of policy.
Item | Excl. VAT | Incl. VAT
Managed Service Retainer (mid-tier of R3,500-R5,500 range) | 4500 | 5175
Recommended Path: Vodacom + Managed Retainer
Recommended Monthly Total (Vodacom + Retainer)
Monthly saving vs Herotel (recommended path, incl. VAT)
Monthly saving vs Herotel (Vodacom-only, self-maintained, incl. VAT)

## 4. 10-Year Cash Flow
10-Year Cash Flow — Build vs Keep Renting
Year 0 = build year (deposit and construction). Years 1-10 = the network's expected working life under CTTX support. All figures incl. VAT.
Annual escalation rate (applied to both Herotel and Vodacom monthly fees) | 8% | <- editable assumption; see tab 5 for why 8% was used
Year | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Path A: Stay with Herotel (do nothing)
Herotel monthly bill (escalated)
Herotel annual cost
Herotel cumulative cost
Path B: Build the CTTX private network (recommended - Vodacom + Managed Retainer)
Build cost (one-time, Year 0 only) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vodacom once-off connection fee (Year 0 only) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CTTX monthly recurring (Vodacom + Retainer, escalated) | 0
CTTX annual recurring cost
CTTX cumulative cost
Cumulative Savings (Path A minus Path B)
Cumulative savings from building (negative = still paying off the build)
Payback Calculation
Last year cumulative savings still negative or zero (position in range)
That year number
Cumulative savings at that year
Cumulative savings the following year
Payback point (years, decimal)
Payback point (plain English)
Total 10-year saving vs Herotel (recommended path)

## 5. Assumptions & Scope
Assumptions, Scope, and What's Not Yet Confirmed
Financial Assumptions
Assumption | Value | Basis
Annual price escalation (Herotel and Vodacom) | 8% p.a. | Not confirmed by either party - a typical CPI-linked telecom escalation in South Africa. Editable on tab 4; change it and every formula recalculates.
Contingency on build cost | 10% | Standard CTTX estimating practice for a project at this stage (pre-final-survey).
VAT rate | 15% | Current South African VAT rate.
Managed Service Retainer | R4,500/month excl. VAT | Mid-point of CTTX's R3,500-R5,500/month range for a system this complex (mast, solar/battery, 30 radios).
Contract term - Vodacom Business Connect | 24 months | Standard Vodacom Business Connect contract term. The network's physical life (10 years) is longer than this contract term - Vodacom connectivity is expected to be renewed at then-current rates.
Design Assumptions
Single 9m mast carrying two 90-degree sector antennas (confirmed by Gerhard, 26 Sept 2026) - replaces the lodge's existing leaning gum-pole mount. This is NOT a two-site build; earlier drafts of this costing incorrectly read the field survey's two radio labels as two separate physical locations before this was corrected.
Line-of-sight confirmed for all 28 subscriber links by Abel Ringisai's field RF survey (KML export, 22 Sept 2026).
The longest links (1.7km-3.0km, to the staff village and Director's House) sit at the edge of the serving sector's range and still need a link-budget check to confirm they sustain full 100 Mbps symmetrical - flagged, not yet resolved.
Cable run priced at an average 40m per run - to be confirmed once exact distances are measured on site.
Vodacom Business Connect feasibility for this specific site has not yet been formally submitted/approved.
What's Included in the 10-Year Support
Years 1-3: monthly remote monitoring, quarterly on-site maintenance, 24/7 emergency support, proactive performance reporting, warranty-covered equipment troubleshooting/replacement.
Years 4-10: ongoing remote monitoring, annual on-site maintenance/assessment, 24/7 support continuation, planned technology refresh, performance reporting.
Throughout: no vendor lock-in on the owned hardware, scalability support, staff training and documentation.
What's Excluded / Not Yet Priced
Major component replacement (Lithium battery bank, inverter) near the end of the 10-year term - typical service life for this equipment is 8-10 years, so a replacement reserve may be needed in years 8-10 and is not included in the build cost above.
Trenching or underground civil works (none required - this is a wireless solution).
CCTV cameras, POS hardware, or other endpoint devices not listed in the hardware BOM.
Travel/accommodation beyond a day-trip assumption from Port Elizabeth (~1h45 drive) - to be confirmed if overnight stays are required during the 3-day install.
Any scope beyond the confirmed coverage zones (28 subscriber sites) without a signed change order.